## Change Tracker
THANOS WALLET - Change & Suggestion Tracker
Updated 2026-06-18 - Web is LIVE & verified current - Mobile in APK build fceaee9b - Extension in rebuilt zip 0.2.0
# | Date | Platform | Type | Request / Suggestion | What was done | Status | Commit | Delivery
1 | 2026-06-16 | Mobile | Feature | Market screen (live prices, 24h/7d %, cap, vol) | Built MarketScreen + market-quotes data | Completed | a1623b8 | In APK fceaee9b
2 | 2026-06-16 | Mobile | Feature | Assets screen with allocation donut | Built AssetsScreen + SVG donut | Completed | 1c815d9 | In APK fceaee9b
3 | 2026-06-16 | Mobile | Feature | Token detail: Buy + circulating supply | Added Buy + supply row | Completed | 1443f19 | In APK fceaee9b
4 | 2026-06-16 | Mobile | Feature | Multi-account switcher | Verified existing header switcher | Completed | existing | In APK fceaee9b
5 | 2026-06-16 | Mobile | Feature | NFTs screen | NFTs screen (honest empty + marketplace) | Completed | 0b3e718 | In APK fceaee9b
6 | 2026-06-16 | Mobile | Feature | Currency / Language / Theme settings | Added General settings section | Completed | 7c73f1e | In APK fceaee9b
7 | 2026-06-16 | Mobile | Feature | DNNS .litho registration | DnnsModal + lib/dnns (resolve/reverse/register) | Completed | fa00512 | In APK fceaee9b
8 | 2026-06-16 | Mobile | Feature | Private-key import (EVM-only) | Import-choose + import-pk flow | Completed | 5a5bfe4 | In APK fceaee9b
9 | 2026-06-16 | Mobile | Feature | Cloud account sign-in | AccountModal (login/register/logout) | Completed | d2ea489 | In APK fceaee9b
10 | 2026-06-16 | Mobile | Feature | Hardware wallet (Ledger/Trezor) | Honest entry; full BLE = separate native build | Roadmap | b52c2fe | In APK fceaee9b
11 | 2026-06-15 | Mobile | Bug | Stuck on 'Encrypting' (first Argon2 attempt) | Argon2 19MiB (still too slow on weak device) | Completed | 13edfb9 | Superseded by PBKDF2
12 | 2026-06-18 | Mobile | Bug | Encryption took 5-10 MIN / app crashed | KDF Argon2 -> PBKDF2 600k (~1-3s) | Completed | 4a14a85 | In APK fceaee9b
13 | 2026-06-18 | Mobile | Bug | Splash light->dark flash + logo not showing | Dark splash bg (#080809) + userInterfaceStyle dark | Completed | 2980848 | In APK fceaee9b
14 | 2026-06-18 | Mobile | Bug | 'I understand' / 'Create wallet' buttons wrapped | numberOfLines + adjustsFontSizeToFit + wider btn | Completed | 4a14a85 | In APK fceaee9b
15 | 2026-06-15 | Mobile | Feature | Choose 12 / 24-word phrase length | Added create-length step | Completed | 13edfb9 | In APK fceaee9b
16 | 2026-06-15 | Mobile | Bug | Onboarding buttons untappable w/ keyboard | keyboardShouldPersistTaps=handled | Completed | a7e6571 | In APK fceaee9b
17 | 2026-06-15 | Mobile | UI | Onboarding usability + dark default + colors | Dark-first, palette, audit fixes | Completed | ca035c7 | In APK fceaee9b
18 | 2026-06-16 | Mobile | Asset | Discover logos + ecosystem sync | Makalu/Kamet entries + Infra section + logos | Completed | 17ff5ea | In APK fceaee9b
19 | 2026-06-17 | Mobile | Feature | LITHO currency symbol | Embedded LithoSym font via expo-font plugin | Completed | 427db10 | In APK fceaee9b
20 | 2026-06-18 | Mobile | Feature | Receive: network -> asset -> QR (SafePal) | Step flow + asset name/logo + coin warning | Completed | 32739c1 | In APK fceaee9b
21 | 2026-06-18 | Mobile | Feature | Cross-chain swap (tabs + chains + recipient) | Swap/Cross-chain/Bridge tabs, indicative rate | Completed | 26002e8 | In APK fceaee9b
22 | 2026-06-17 | Web | Bug | Cosmos Hub send showed LITHO icon | Map cosmos->ATOM + add ATOM logo | Completed | d1c9473 | LIVE
23 | 2026-06-17 | Web | Feature | Swap stablecoin pairs w/ fixed rates | LAX/USDC.USDT.DAI + stable-stable | Completed | 8f76cf7 | LIVE
24 | 2026-06-17 | Web | UI | Swap full-screen from nav (popup from Home) | fullScreen Modal variant + entry split | Completed | 61fc516 | LIVE
25 | 2026-06-18 | Web | Feature | Receive: network -> asset -> QR (SafePal) | Drill-in network->asset->QR + asset header | Completed | 159ffe9 | LIVE
26 | 2026-06-18 | Web | Feature | Receive preselects network from an asset | Token-detail Receive jumps to that asset's QR | Completed | 949686a | LIVE
27 | 2026-06-17 | Web | Bug | Discover screen scroll issue | Made Discover scroll (main overflow:hidden) | Completed | 9ee0eee | LIVE
28 | 2026-06-17 | Web | Asset | Discover logos (Makalu/Kamet/LITHO Deals) | Wired client app-icon pack | Completed | da8d0aa | LIVE
29 | 2026-06-17 | Web | Feature | LITHO currency symbol (bundled font) | Single-glyph font + LithoSym component | Completed | 18147e3 | LIVE
30 | 2026-06-17 | Cross | Pricing | Prices from CoinGecko (non-fixed tokens) | MUSA live via mansa-ai; JOT/BLDR/FGPT unlisted | Completed | bc0d694 | LIVE
31 | 2026-06-18 | Cross | Pricing | LITHO fixed price -> $8.82 (LAX $1.0001) | Updated web/mobile/sdk-core/worker | Completed | 268c4ba | LIVE
32 | 2026-06-18 | Web | Feature | Cross-chain swap UI (tabs + chains + recipient) | Swap/Cross-chain/Bridge tabs, live indicative rate | Completed | 1c94f53 | LIVE
33 | 2026-06-16 | Web | UI | Token detail as full-screen page | Trust/SafePal-style full-screen | Completed | 99d0dce | LIVE
34 | 2026-06-17 | Landing | UI | 25% UI increase (125%) incl. landing + mobile | body zoom 1.25 + landing mobile zoom | Completed | a886df9 | LIVE
35 | 2026-06-17 | Landing | Feature | APK direct download on thanos.fi | /download route -> streams thanos.apk | Completed | 7e1dd1d | LIVE
36 | 2026-06-17 | Landing | Bug | 'Download .apk' card not clickable | Android card live -> /download | Completed | b5819fb | LIVE
37 | 2026-06-17 | Landing | UI | APK downloads as thanos.apk (professional) | Content-Disposition filename=thanos.apk | Completed | 4f7c6aa | LIVE
38 | 2026-06-18 | Landing | Chore | Point /download at the CURRENT build | APK_URL -> build fceaee9b (verified byte-match live) | Completed | fb22b18 | LIVE
39 | 2026-06-18 | Web/Ext | Perf | Wallet create/unlock took several seconds | Vault KDF -> native WebCrypto PBKDF2 600k (~100ms) | Completed | 988eab4 | Web LIVE / Ext in zip
40 | 2026-06-18 | Ext | Perf | Extension slow to create/unlock (like the app) | Argon2 64MiB -> native PBKDF2 600k | Completed | 988eab4 | In ext zip 0.2.0
41 | 2026-06-18 | Ext | Feature | Receive: network -> asset -> QR (SafePal) | Step flow + asset header + coin warning | Completed | 6d6f780 | In ext zip 0.2.0
42 | 2026-06-18 | Ext | Feature | Cross-chain swap (tabs + chains + recipient) | Swap/Cross-chain/Bridge tabs, indicative rate | Completed | 0ee7a24 | In ext zip 0.2.0
43 | 2026-06-16 | Backend | Config | Apply Litho canonical values | Kamet explorer, IMAGE name, cleanup | Completed | e7cb761 | LIVE
44 | 2026-06-16 | CI | Bug | Red CI (frozen lockfile + gitleaks) | --no-frozen-lockfile + gitleaks allowlist | Completed | aa08aed | LIVE
45 | 2026-06-16 | Mobile | Build | APK pipeline (lockfile / minify / config) | Linux lockfile, R8 off, expo-build-properties | Completed | ecb1d9d+ | Resolved
46 | 2026-06-17 | Cross | Audit | Confirm production-stage feature set (13) | Verified each vs code; status table | Completed | audit | Delivered
47 | 2026-06-18 | Mobile | Build | Rebuild APK with all fixes + ports | EAS build fceaee9b | Completed | build | Delivered + on thanos.fi/download
48 | 2026-06-18 | Ext | Build | Rebuild extension zip | wxt zip -> thanosextension-0.2.0-chrome.zip | Completed | build | Delivered (6.97 MB)
49 | 2026-06-17 | Cross | Decision | LITHO & LAX fixed (not fetched) | LITHO $8.82, LAX $1.0001; ego.exchange noted | Decision | - | Policy
50 | 2026-06-18 | Cross | Decision | Cross-chain execution gated on MultX bridge | UI complete on all clients; exec when bridge live | Decision | - | Roadmap (Litho infra)

## Summary
Summary
Total tracked items | 50
Completed | 47
Decisions / policy | 2
Roadmap | 1
Web | LIVE & verified current on thanos.fi
Mobile | APK build fceaee9b - install link + on thanos.fi/download
Extension | rebuilt zip thanosextension-0.2.0-chrome.zip
APK install link | expo.dev/accounts/imasssad/projects/thanos-wallet/builds/fceaee9b-f3ce-4ab8-b720-a5774643d135
Note | Cross-chain swap UI done on all 3 clients; execution unlocks when the MultX bridge backend is online (Litho infra).